## Budget
Cost_ID | Workstream | Baseline_CAD | Illustrative_EAC_W16_CAD | Explanation
B-01 | Discovery and requirements | 28000 | 28000 | Base work
B-02 | Solution design | 28000 | 28000 | Base work
B-03 | Development and integration | 86000 | 86000 | Base work
B-04 | QA and UAT | 34000 | 34000 | Base work
B-05 | Training and change | 23000 | 23000 | Base work
B-06 | Deployment and hypercare | 13000 | 13000 | Base work
B-07 | PM and governance | 16000 | 16000 | Base work
B-08 | Contingency | 12000 | 8000 | CHG-01 approved draw; 4000 unspent

## Milestones
ID | Phase | Milestone | Baseline_Week | Forecast_Week | Scenario_Status_W16 | Owner | Dependency | Gate_Evidence
M-01 | Initiation | Concept authorized | 2 | 2 | Complete | Sponsor |  | Business case
M-02 | Planning | Baseline scope and plan approved | 5 | 5 | Complete | Sponsor | M-01 | Charter + WBS + budget
M-03 | Build | Features baseline complete | 13 | 13 | Complete | Technical Lead | M-02 | Demo + traceability
M-04 | Assurance | UAT and operations gate | 17 | 17 | At risk | Business Owner / Ops Lead | M-03 | UAT >=95%; zero P0/P1; readiness checklist
M-05 | Release | 10-school pilot | 18 | 18 | At risk | Sponsor | M-04 | G3 go/no-go + smoke tests
M-06 | Pilot | Pilot evidence and decision | 20 | 20 | Planned | Sponsor | M-05 | Support + adoption + incident evidence
M-07 | Release | 40-school expanded rollout | 21 | 21 | Planned | Sponsor | M-06 | G4 go/no-go + readiness
M-08 | Closure | Handover and closeout | 24 | 24 | Planned | Business Owner / Ops Lead | M-07 | Runbook + benefits ownership + closure

## RAID
Record_ID | Type | Description | Likelihood_1to5 | Impact_1to5 | Score | Priority | Owner | Response_or_Action | Target_Week | Status_W16 | Scenario_Resolution
R-01 | Risk | Duplicate candidate IDs in legacy import | 4 | 5 | 20 | High | Data Lead | Profile source; dry-run reconciliation; negative tests | 16 | Materialized as I-01 | See I-01; closed W17 in worked scenario
R-02 | Risk | Limited school UAT capacity | 3 | 4 | 12 | Medium | Business Owner | Reserve testers and alternates | 14 | Mitigating | No delay simulated
R-03 | Risk | Incorrect access to school records | 2 | 5 | 10 | Medium | Technical Lead | Permission review and negative-case UAT | 17 | Mitigating | Access gate passed W17
R-04 | Risk | Training below release target | 3 | 3 | 9 | Medium | Change Lead | Train-the-trainer and attendance tracking | 17 | Mitigating | 95% sample completion at closure
A-01 | Assumption | School SMEs available for UAT | 0 | 0 | 0 | Watch | Business Owner | Validate participant commitments | 13 | Validated | Confirmed in simulation
D-01 | Dependency | Approved source-to-target data mapping | 0 | 0 | 0 | High | Data Lead | Get business owner approval | 16 | At risk | Remediated and signed W17
I-01 | Issue | Duplicate candidate IDs fail migration rehearsal and UAT | 0 | 5 | 0 | Critical | Data Lead | Quarantine; revise mapping; retest; CHG-01 DEC-02 | 17 | Open P1 | Closed after 180/180 pass W17

## Requirements
Requirement_ID | Business_Need | Priority | Acceptance_Criterion | Test_Ref | W16_Status | W17_Simulated_Status | Owner
REQ-01 | School profile and authorized users | Must | Users isolated to permitted schools | UAT-01 | Pass | Pass | Business Owner
REQ-02 | Candidate form and mandatory fields | Must | Required fields enforced | UAT-02 | Pass | Pass | Business Owner
REQ-03 | Exam selection | Must | Only eligible selections allowed | UAT-03 | Pass | Pass | Business Owner
REQ-04 | Duplicate record validation | Must | Duplicates rejected or quarantined | UAT-04 | Fail P1 | Pass | Business Owner
REQ-05 | Registration confirmation | Must | Stable confirmation ID generated | UAT-05 | Pass | Pass | Business Owner
REQ-06 | Access controls and audit | Must | Unauthorized access denied and logged | UAT-06 | Pass | Pass | Business Owner
REQ-07 | Operational export | Should | Report reconciles with accepted records | UAT-07 | Pass | Pass | Business Owner
REQ-08 | Validated legacy roster import | Should | Exception reporting and reconcilable totals | UAT-08 | Blocked | Pass | Business Owner

## Test_Cases
Test_ID | Requirement_ID | Scenario | Expected_Result | W16_Result | W17_Result | Severity_if_Failed | Evidence
UAT-01 | REQ-01 | School user opens candidate from another school | Access denied | Pass | Pass | P1 | SYN-001
UAT-02 | REQ-02 | Submit with missing required identity field | Block with message | Pass | Pass | P2 | SYN-002
UAT-03 | REQ-03 | Select ineligible examination | Selection rejected | Pass | Pass | P2 | SYN-003
UAT-04 | REQ-04 | Import duplicate candidate identifier | Quarantine and log duplicate | Fail | Pass | P1 | SYN-004
UAT-05 | REQ-05 | Complete successful enrolment | Issue repeatable confirmation | Pass | Pass | P2 | SYN-005
UAT-06 | REQ-06 | Attempt unprivileged update | Deny and audit | Pass | Pass | P1 | SYN-006
UAT-07 | REQ-07 | Export accepted enrolments | Reconciled counts | Pass | Pass | P2 | SYN-007
UAT-08 | REQ-08 | Import legacy sample roster | Matched totals; exceptions logged | Blocked | Pass | P1 | SYN-008

## Stakeholders
Role | Influence | Interest | Primary_Need | Engagement_Strategy | Cadence
Sponsor | High | High | Business outcomes; budget; gates | Manage closely; decision brief | Biweekly + critical issue
Business Owner | High | High | Usable workflows; acceptance | Workshops; UAT; signoff | Weekly
School Representatives | Medium | High | Usable registration and training | Pilot champions; demos | At milestones
Technical Lead | High | High | Feasible design and dependencies | Integrated review; decision input | Daily + weekly
QA Lead | High | High | Test evidence; exit criteria | Defect triage and quality gate | Daily in UAT
Data Lead | Medium | High | Mapping and reconciliation | Migration reviews | Weekly; daily during cutover
Operations Lead | High | High | Supportable release and handover | Readiness and hypercare reviews | Weekly from W14
Change Lead | Medium | Medium | Training and communication | Adoption tracking | Weekly

## RACI
Activity | Sponsor | Business_Owner | Project_Manager | Technical_Lead | QA_Lead | Data_Lead | Operations_Lead | Change_Lead
Approve project baseline | A | C | R | C | I | I | I | I
Sign off business requirements | I | A | C | C | C | I | I | I
Maintain integrated schedule and RAID | I | C | A/R | C | C | C | C | C
Approve technical design | I | C | I | A/R | C | C | C | I
Approve UAT acceptance | I | A | C | C | R | C | C | I
Approve contingency draw | A | C | R | C | C | C | I | I
Execute migration | I | C | C | C | C | A/R | C | I
Authorize go/no-go | A | R | C | C | C | C | R | I
Accept operational handover | I | C | C | C | C | C | A/R | R

## Decisions
ID | Record_Type | Raised_Week | Description | Decision_Owner | Status | Cost_Impact_CAD | Schedule_Impact | Linked_Item
DEC-01 | Decision | 5 | Approve 24-week baseline and CAD 240000 total ceiling | Sponsor | Approved (simulation) | 0 | Baseline agreed | M-02
CHG-01 | Change | 16 | Targeted mapping remediation and QA retest within existing scope | Sponsor | Approved (simulation) | 8000 | No rebaseline; W17 gated | I-01
DEC-02 | Decision | 16 | Approve 8000 contingency draw; preserve quality gate | Sponsor | Approved (simulation) | 8000 | W18 still conditional | CHG-01
DEC-03 | Decision | 17 | Approve pilot only after 180 of 180 UAT cases pass and Ops review | Sponsor | Approved (simulation) | 0 | Pilot W18 | M-04
DEC-04 | Decision | 20 | Approve 40-school expansion after pilot review | Sponsor | Approved (simulation) | 0 | Expansion W21 | M-06

## Actions
Action_ID | Raised_Week | Action | Owner | Due_Week | Status_at_W16 | Linked_Record
ACT-01 | 16 | Revise duplicate identifier mapping | Data Lead | 17 | Open | I-01
ACT-02 | 16 | Retest 180 UAT scenarios and report P1 status | QA Lead | 17 | Open | I-01
ACT-03 | 16 | Escalate contingency request and gate risk | Project Manager | 16 | Done | CHG-01
ACT-04 | 16 | Verify pilot support and rollback steps | Operations Lead | 17 | Open | M-04
ACT-05 | 16 | Coordinate school pilot training confirmation | Change Lead | 17 | In progress | M-05

## Cutover
Check_ID | Go_Live_Gate | Check | Evidence_Owner | W16_Status | W17_Scenario_Status | Notes
G3-01 | W17 | UAT 95 percent or above; zero P0/P1 | QA Lead | Blocked | Pass | 180/180 pass W17 in simulation
G3-02 | W17 | Data mappings reconciled and exceptions dispositioned | Data Lead | Blocked | Pass | REQ-04 and REQ-08
G3-03 | W17 | Role access security tests accepted | Technical Lead | In review | Pass | Negative tests
G3-04 | W17 | School training and support plan confirmed | Change Lead | In progress | Pass | Pre-pilot readiness
G3-05 | W17 | Runbook rollback and contacts verified | Operations Lead | In review | Pass | Service owner assigned
G3-06 | W17 | Sponsor pilot go/no-go signed | Sponsor | Not started | Pass | DEC-03
G4-01 | W20 | Pilot adoption incidents and data quality reviewed | Operations Lead | Not started | Pass W20 | DEC-04
G5-01 | W24 | Service acceptance and residual risks transferred | Operations Lead | Not started | Pass W24 | Illustrative closeout

## Benefits
Benefit_ID | Metric | Target | Simulation_W24_Result | Measurement_Method | Owner | Followup
BEN-01 | Eligible registration completion rate | >=95% | 97.8% | Accepted/eligible submissions in sample window | Business Owner | 30 60 90 days post release
BEN-02 | School staff training completion | >=90% | 95% | Completed learning checks / planned attendees | Change Lead | At release gate and after launch
BEN-03 | Critical defect exit | 0 open P0/P1 | 0 | QA defect report | QA Lead | Each release gate
BEN-04 | Spending against cap | <=240000 CAD | 236000 CAD | Cost tracker including approved reserve draw | Sponsor | Closure

## UAT_Summary
Checkpoint | Planned | Passed | Failed | Blocked | Pass_Rate | P0_P1_Open
W16 | 180 | 169 | 5 | 6 | 93.89% | 1
W17 | 180 | 180 | 0 | 0 | 100% | 0

## Dashboard
STUDENT ENROLMENT ¦ PMO DELIVERY CONTROL
MARTINS AJAYI · WORKED CASE STUDY · ALL DATA BELOW ILLUSTRATIVE, NOT HISTORICAL
CONTROL METRIC | SCENARIO VALUE
Approved total ceiling (CAD) | 240000
Forecast at completion (CAD) | 236000
Unspent reserve/headroom (CAD) | 4000
W16 UAT pass rate | 93.89%
W17 UAT pass rate | 100%
W16 open critical defects | 1
W17 open critical defects | 0
Pilot week | 18
Expanded rollout week | 21
W16 GOVERNANCE EXCEPTION: Amber due to import duplicate issue I-01 (P1).
CHG-01/DEC-02: Approve CAD 8,000 reserve draw; no release without passed W17 gate.
NOTICE: All volumes, schedules, finances, test outcomes and approvals are reconstructed illustrative data. No employers or client organizations are disclosed.

## Backlog
Story_ID | Requirement | Priority | Iteration_Example | Story_or_Feature | Acceptance_Evidence | Scenario_Demo_Status | Owner
ST-01 | REQ-02 | Must | W8-W10 | Candidate registration entry | Negative mandatory-field validation | Accepted for integration | Delivery Lead
ST-02 | REQ-03 | Must | W8-W10 | Examination selection rules | Eligible exam choice tests | Accepted with copy edit | Business Owner
ST-03 | REQ-05 | Must | W8-W10 | Confirmation references | Repeatable confirmation ID | Accepted for integration | QA Lead
ST-04 | REQ-04 | Must | W8-W10 | Duplicate record guardrails | Manual and bulk import duplicate tests | Additional regression required | Data Lead
ST-05 | REQ-06 | Must | W11-W13 | Role-based access audit | Negative access test and audit proof | Build complete | Technical Lead