## Overview
Pension administration review
Illustrative scenario. Cost snapshot W24; release evidence W26.
Metric | Calculated result | Basis
Funding ceiling CAD | 480000 | Base plus reserve
Estimated actual CAD | 370000 | Estimated scenario cost
Remaining forecast CAD | 98000 | Includes approved reserve draw once
EAC CAD | 468000 | Actual plus remaining
Funding headroom CAD | 12000 | Ceiling less EAC
Mandatory gates passed | 6 | W26 simulated controls
Evidence state | Ready for evidence review | Review authentic evidence and authorization separately

## Schedule
Pension administration controls
Illustrative reconstruction. All figures and evidence references are fictional.
ID | Milestone | Baseline week | Forecast week | Owner | Dependency
P-M01 | Charter and rules | 6 | 6 | Sponsor
P-M02 | Design approved | 10 | 10 | Technical Lead | P-M01
P-M03 | Build baseline | 20 | 20 | Technical Lead | P-M02
P-M04 | UAT and migration gate | 25 | 26 | Business Owner | P-M03
P-M05 | Pilot | 26 | 27 | Sponsor | P-M04
P-M06 | Expansion review | 27 | 28 | Sponsor | P-M05
P-M07 | Expanded access | 28 | 29 | Operations Lead | P-M06
P-M08 | Handover and closure | 32 | 32 | Operations Lead | P-M07

## Budget
Pension administration controls
Illustrative reconstruction. All figures and evidence references are fictional.
ID | Workstream | Baseline CAD | Actual CAD | Remaining CAD | Forecast CAD
P-B01 | Discovery and rules | 45000 | 45000 | 0 | 45000
P-B02 | Design | 55000 | 55000 | 0 | 55000
P-B03 | Build and integrations | 160000 | 150000 | 10000 | 160000
P-B04 | Migration and reconciliation | 65000 | 45000 | 20000 | 65000
P-B05 | QA and assurance | 50000 | 35000 | 15000 | 50000
P-B06 | Training and transition | 40000 | 15000 | 25000 | 40000
P-B07 | Governance | 35000 | 25000 | 10000 | 35000
P-B08 | Contingency | 30000 | 0 | 18000 | 18000
| Total | 480000 | 370000 | 98000 | 468000

## RAID
Pension administration controls
Illustrative reconstruction. All figures and evidence references are fictional.
ID | Type | Description | Owner | Status W24 | Action | Due week | Link
R-P01 | Risk | Incorrect identity linkage | Data Lead | Materialized | Profile keys and reconcile | 26 | I-P01
I-P01 | Issue | Rehearsal mislinks service history | Data Lead | Open P1 | Freeze output; correct; retest | 26 | CR-P01
R-P02 | Risk | Unapproved eligibility interpretation | Business Owner | Mitigating | Policy-owner boundary examples | 10 | PEN-03
R-P03 | Risk | Inadequate role separation | Technical Lead | Mitigating | Negative approval and access tests | 26 | PEN-04
A-P01 | Assumption | Policy SMEs available for acceptance | Business Owner | Confirmed | Reserve alternates | 23 | P-M04
D-P01 | Dependency | Signed source-to-target map | Finance Controller | At risk | Independent reconciliation | 26 | P-G02

## Traceability
Pension administration controls
Illustrative reconstruction. All figures and evidence references are fictional.
Requirement | Acceptance criterion | Test | Owner | W24 result | W26 result | Illustrative evidence
PEN-01 | Duplicate identity rejected | T-P01 | Business Owner | Pass | Pass | SIM-P-T01
PEN-02 | Invalid service dates rejected | T-P02 | Business Owner | Pass | Pass | SIM-P-T02
PEN-03 | Calculation boundary examples correct | T-P03 | Finance Controller | Blocked | Pass | SIM-P-T03
PEN-04 | Originator cannot approve own item | T-P04 | Finance Controller | Pass | Pass | SIM-P-T04
PEN-05 | Unauthorized access denied and audited | T-P05 | Technical Lead | Pass | Pass | SIM-P-T05
PEN-06 | Source accepted and quarantined balance | T-P06 | Data Lead | Fail | Pass | SIM-P-T06
PEN-07 | Replayed status does not duplicate item | T-P07 | Technical Lead | Pass | Pass | SIM-P-T07
PEN-08 | Reports reconcile to accepted records | T-P08 | Finance Controller | Blocked | Pass | SIM-P-T08

## Gates
Pension administration controls
Illustrative reconstruction. All figures and evidence references are fictional.
Gate | Criterion | Owner | W24 status | W26 status | Evidence | Reviewer
P-G01 | UAT >=95%; Must pass; zero P0/P1 | QA Lead | Fail | Pass | SIM-P-UAT-W26 | Business Owner
P-G02 | Counts and values reconcile | Data Lead | Fail | Pass | SIM-P-RECON-W26 | Finance Controller
P-G03 | Access and maker-checker verified | Technical Lead | Pass | Pass | SIM-P-ACCESS | QA Lead
P-G04 | Training >=90% and critical-role cover | Change Lead | Pending | Pass | SIM-P-TRAIN | Business Owner
P-G05 | Runbook restore and support accepted | Operations Lead | Pending | Pass | SIM-P-OPS | Operations Lead
P-G06 | Pilot decision recorded | PM | Pending | Pass | DEC-P02 | Sponsor