## Overview
Network design review
Illustrative scenario. Cost snapshot W11; handoff evidence W16.
Metric | Calculated result | Basis
Funding ceiling CAD | 120000 | Base plus reserve
Estimated actual CAD | 86000 | Estimated scenario cost
Remaining forecast CAD | 30000 | Includes approved reserve draw once
EAC CAD | 116000 | Actual plus remaining
Funding headroom CAD | 4000 | Ceiling less EAC
Mandatory gates passed | 6 | W16 simulated controls
Evidence state | Ready for evidence review | Review authentic evidence and authorization separately

## Schedule
Network application design controls
Illustrative reconstruction. All figures and evidence references are fictional.
ID | Milestone | Baseline week | Forecast week | Owner | Dependency
N-M01 | Discovery charter | 2 | 2 | Sponsor
N-M02 | Research and priority approval | 5 | 5 | Product Owner | N-M01
N-M03 | Prototype baseline | 11 | 11 | UX Lead | N-M02
N-M04 | Final usability and acceptance | 14 | 14 | Product Owner | N-M03
N-M05 | Implementation pack prepared | 15 | 15 | Technical Lead | N-M04
N-M06 | Receive handoff and close | 16 | 16 | Sponsor | N-M05

## Budget
Network application design controls
Illustrative reconstruction. All figures and evidence references are fictional.
ID | Workstream | Baseline CAD | Actual CAD | Remaining CAD | Forecast CAD
N-B01 | Discovery and research | 24000 | 24000 | 0 | 24000
N-B02 | UX design | 32000 | 26000 | 6000 | 32000
N-B03 | Visual and content | 24000 | 18000 | 6000 | 24000
N-B04 | Usability and accessibility | 16000 | 8000 | 8000 | 16000
N-B05 | PM and handoff | 16000 | 10000 | 6000 | 16000
N-B06 | Contingency | 8000 | 0 | 4000 | 4000
| Total | 120000 | 86000 | 30000 | 116000

## Backlog
Network application design controls
Illustrative reconstruction. All figures and evidence references are fictional.
Story | Requirement | Priority | Acceptance | Owner | Final status | Decision
N-ST01 | NET-01 | Must | Find device and status | UX Lead | Accepted | DEC-N02
N-ST02 | NET-02 | Must | Locate and manage guest control | UX Lead | Accepted after revision | CR-N01
N-ST03 | NET-03 | Must | Find troubleshooting next action | Content Lead | Accepted | DEC-N02
N-ST04 | NET-04 | Must | Restricted action explains permission | UX Lead | Accepted | DEC-N02
N-ST05 | NET-05 | Must | Focus and navigation reviewed | QA Reviewer | Accepted | DEC-N02
N-ST06 | New request | Later | Usage history needs backend discovery | Product Owner | Deferred | CR-N02

## Research
Network application design controls
Illustrative reconstruction. All figures and evidence references are fictional.
Task | Requirement | Baseline success | Baseline sample | Final success | Final sample | Final rate | Target | Gate
RES-01 | NET-01 | 7 | 12 | 11 | 12 | 91.67% | 80% | Meets
RES-02 | NET-02 | 6 | 12 | 10 | 12 | 83.33% | 80% | Meets
RES-03 | NET-03 | 8 | 12 | 11 | 12 | 91.67% | 80% | Meets

## Gates
Network application design controls
Illustrative reconstruction. All figures and evidence references are fictional.
Gate | Criterion | Owner | W11 status | W14 status | W16 status | Evidence | Reviewer
N-G01 | Device task >=80% | Research Lead | Pending | Pass | Pass | SIM-N-RES01 | Product Owner
N-G02 | Guest control task >=80% | Research Lead | Fail | Pass | Pass | SIM-N-RES02 | Product Owner
N-G03 | Troubleshooting task >=80% | Research Lead | Pending | Pass | Pass | SIM-N-RES03 | Product Owner
N-G04 | Zero critical findings and reviewed accessibility | QA Reviewer | Pending | Pass | Pass | SIM-N-QA | QA Reviewer
N-G05 | Feasibility and prototype acceptance | Technical Lead | Pending | Pass | Pass | DEC-N02 | Product Owner
N-G06 | Receiving-team handoff W16 | PM | Pending | Pending | Pass | DEC-N03 | Technical Lead

## RAID
Network application design controls
Illustrative reconstruction. All figures and evidence references are fictional.
ID | Type | Description | Owner | Status W11 | Action | Due week | Link
R-N01 | Risk | Feature interest may not mean task success | Research Lead | Materialized | Observe task attempts | 13 | I-N01
I-N01 | Issue | Guest journey only 6 of 12 succeed | UX Lead | Open critical | Revise content and navigation | 13 | CR-N01
R-N02 | Risk | Unsupported device capability implied | Technical Lead | Mitigating | Feasibility review | 14 | N-G05
R-N03 | Risk | Research sample bias | Research Lead | Mitigating | Record mix and learning effects | 14 | RES-02
D-N01 | Dependency | Receiving-team capacity | Technical Lead | Confirmed | Reserve handoff review | 16 | N-G06